## ORder
| POWERBI DATA - LEGACY | [11 empty] | NEW - BOOKING/SCHEDULE
RESOURCE GROUP | Resource | SALESORDERNUMBER | SALESORDERNAME | ITEMNUMBER | ORDER | STATUS | PRODUCTION Start Date | START CADENCE | ASSY START DATE (+5 WK Days) | PRODUCTION ORDER DELIVERY DATE | ASSY/CAL/COMPLETE DAYS | SC3 | ALLOCATED RESOURCE | ALLOCATED PROD ORDER | STATUS | PRODUCTION START | Pick | ASSY START | Assy | ASSY END | SHIP DATE | MATERIAL KPI | DELIVERY KPI | Flow Time (Working Days) | Active Days | Continuity %
FA-300SL | 366448/W/H-End// Started/1 | 701276 | Fairbanks Morse Defense | 09001300 | 366448 | STARTED | 2026-05-29 |  |  | 2026-06-16 |  | 300SL | W/H_END | 366448 | STARTED | 2026-05-29 | 2 | 2026-06-02 | 10 | 2026-06-16 | 2026-06-30 | ON TIME |  | = NETWORKDAYS(First Posting, Last Posting) | Posted days | Active Posting Days ÷ Flow Time
FA-300SL | 366127/Assembly/Assy07/ Started/1 | 700470 | Element | 09001300 | 366127 | STARTED | 2026-06-10 | 9 | 2026-06-17 | 2026-07-02 | 12 | 300SL | CAL_GEN | 366127 | STARTED | 2026-06-10 | 5 | 2026-06-17 | 15 | 2026-07-08 | 2026-07-22 | LATE
FA-300SL | 366204/W/H-Start/GenElec/ Released/1 | 700525 | Nucor Towers and Structures | 09001300 | 366204 | STARTED | 2026-06-17 | 6 | 2026-06-24 | 2026-07-24 | 23 | 300SL | ASSY07 | 366204 | STARTED | 2026-06-24 | 5 | 2026-07-01 | 15 | 2026-07-22 | 2026-08-05
FA-300SL | 364885/W/H-Start/GenAssy/ Released/1 | 593042 | DFAS ROCK ISLAND - HQ0303 | 09001330 | 364885 |  | 2026-07-09 | 17 | 2026-07-16 | 2026-08-13 | 21 | 300SL |  |  | Released | 2026-07-08 | 5 | 2026-07-15 | 15 | 2026-08-05 | 2026-08-19
FA-300SL | 364886/W/H-Start/GenAssy/ Released/1 | 593042 | DFAS ROCK ISLAND - HQ0303 | 09001330 | 364886 |  | 2026-07-21 | 9 | 2026-07-28 | 2026-08-25 | 21 | 300SL |  |  | Released | 2026-07-22 | 5 | 2026-07-29 | 15 | 2026-08-19 | 2026-09-02
FA-300SL | 366208/W/H-Start/GenElec/ Released/1 | 700527 | Nucor Towers and Structures | 09001300 | 366208 |  | 2026-08-12 | 17 | 2026-08-19 | 2026-09-16 | 21 | 300SL |  |  | Released | 2026-08-05 | 5 | 2026-08-12 | 15 | 2026-09-02 | 2026-09-16
FA-300SL | 366129/Electrical/GenElec/ Started/1 | 700471 | Element | 09001300 | 366129 |  | 2026-09-03 | 17 | 2026-09-10 | 2026-09-24 | 11 | 300SL |  |  | Released | 2026-08-19 | 5 | 2026-08-26 | 15 | 2026-09-16 | 2026-09-30
FA-300SL | 365843/W/H-Start/GenAssy/ Released/1 | 596793 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09001310 | 365843 |  | 2026-09-15 | 9 | 2026-09-22 | 2026-10-20 | 21 | 300SL |  |  | Released | 2026-09-02 | 5 | 2026-09-09 | 15 | 2026-09-30 | 2026-10-14
FA-300SL | 365846/W/H-Start/GenAssy/ Released/1 | 596793 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09001310 | 365846 |  | 2026-10-01 | 13 | 2026-10-08 | 2026-11-05 | 21 | 300SL |  |  | Released | 2026-09-16 | 5 | 2026-09-23 | 15 | 2026-10-14 | 2026-10-28
FA-300SL | 366541/W/H-Start/GenAssy/ Released/1 | 701595 | CEMEX | 09001320 | 366541 |  | 2026-10-16 | 12 | 2026-10-23 | 2026-11-20 | 21 | 300SL |  |  | Released | 2026-09-30 | 5 | 2026-10-07 | 15 | 2026-10-28 | 2026-11-11
FA-300SL | 366212/W/H-Start/GenElec/ Released/1 | 700529 | Nucor Steel Company | 09001300 | 366212 |  | 2026-10-19 | 2 | 2026-10-26 | 2026-11-23 | 21 | 300SL |  |  | Released | 2026-10-14 | 5 | 2026-10-21 | 15 | 2026-11-11 | 2026-11-25
FA-300SL | 365168/W/H-Start/W/H-Start/ Released/1 | 596507 | Element | 09001300 | 365168 |  | 2026-11-02 | 11 | 2026-11-09 | 2026-12-09 | 23 | 300SL |  |  | Released | 2026-10-28 | 5 | 2026-11-04 | 15 | 2026-11-25 | 2026-12-09
[16 empty] | 2026-11-11 | 5 | 2026-11-18 | 15 | 2026-12-09 | 2026-12-23
[16 empty] | 2026-11-25 | 5 | 2026-12-02 | 15 | 2026-12-23 | 2027-01-06
FA-600SL | 364091/Calib/Cal_GEN/ Started/1 | 594519 | ACEROS CAMESA SA DE CV | 09002610 | 364091 | STARTED | 2026-03-19 |  | 2026-03-26 | 2026-05-14 | 36 | 600SL | CAL | 364091 | STARTED | 2026-03-19 | 5 | 2026-03-26 | 35 | 2026-05-14 | 2026-05-28 | LATE | LATE
FA-600SL | 364222/Assembly/Assy02/ Started/1 | 594743 | Friedman Industries, Inc. | 09002600 | 364222 | STARTED | 2026-06-05 | 57 | 2026-06-12 | 2026-07-03 | 16 | 600SL | ASSY02 | 364222 | STARTED | 2026-06-05 | 5 | 2026-06-12 | 14 | 2026-07-02 | 2026-07-16 | ON TIME
FA-600SL | 364461/Assembly/Assy10/ Started/1 | 595132 | Taylor Forge | 09002600 | 364461 | STARTED | 2026-06-26 | 16 | 2026-07-03 | 2026-07-24 | 16 | 600SL | ASSY10 | 364461 | STARTED | 2026-06-19 | 5 | 2026-06-26 | 20 | 2026-07-24 | 2026-08-07 | ON TIME
FA-600SL | 365450/W/H-Start/GenAssy/ Released/1 | 596952 | Tinius Olsen Testing Machine Shanghai Co Ltd | 09002620 | 365450 |  | 2026-07-13 | 12 | 2026-07-20 | 2026-08-20 | 24 | 600SL |  |  | Released | 2026-07-03 | 5 | 2026-07-10 | 20 | 2026-08-07 | 2026-08-21
FA-600SL | 365267/W/H-Start/GenAssy/ Released/1 | 596655 | KTH Parts Industries Inc. | 09002600 | 365267 |  | 2026-08-03 | 16 | 2026-08-10 | 2026-09-10 | 24 | 600SL |  |  | Released | 2026-07-17 | 5 | 2026-07-24 | 20 | 2026-08-21 | 2026-09-04
FA-600SL | 366113/W/H-Start/GenAssy/ Released/1 | 700241 | Jennmar Corporation | 09002600 | 366113 |  | 2026-08-24 | 16 | 2026-08-31 | 2026-10-01 | 24 | 600SL |  |  | Released | 2026-07-31 | 5 | 2026-08-07 | 20 | 2026-09-04 | 2026-09-18
FA-600SL | 366477/W/H-Start/GenAssy/ Released/1 | 701140 | Jubail Energy Services Company | 09002610 | 366477 |  | 2026-09-14 | 16 | 2026-09-21 | 2026-11-30 | 51 | 600SL |  |  | Released | 2026-08-14 | 5 | 2026-08-21 | 20 | 2026-09-18 | 2026-10-02
FA-600SL | 366112/W/H-Start/GenAssy/ Released/1 | 700233 | Flash Steelworks | 09002610 | 366112 |  | 2026-10-05 | 16 | 2026-10-12 | 2026-11-12 | 24 | 600SL |  |  | Released | 2026-08-28 | 5 | 2026-09-04 | 20 | 2026-10-02 | 2026-10-16
[16 empty] | 2026-09-11 | 5 | 2026-09-18 | 20 | 2026-10-16 | 2026-10-30
[16 empty] | 2026-09-25 | 5 | 2026-10-02 | 20 | 2026-10-30 | 2026-11-13
[16 empty] | 2026-10-09 | 5 | 2026-10-16 | 20 | 2026-11-13 | 2026-11-27
[16 empty] | 2026-10-23 | 5 | 2026-10-30 | 20 | 2026-11-27 | 2026-12-11
FA-2-2000SL | 364696/Paint/Paint/ Started/1 | 595503 | Gerdau Metaldom S.A. | 09010610 | 364696 | STARTED | 2026-03-31 |  | 2026-04-07 | 2026-06-02 | 41 | 2000SL | PAINT | 364696 | STARTED | 2026-03-31 | 5 | 2026-04-07 | 40 | 2026-06-02 | 2026-06-16 | LATE | LATE
FA-2-2000SL | 365072/Assembly/Assy03/ Started/1 | 596324 | CORINCA CORP IND CENTROAMERICANA | 09010600 | 365072 | STARTED | 2026-06-01 | 45 | 2026-06-08 | 2026-07-23 | 34 | 2000SL | ASSY03 | 365072 | STARTED | 2026-06-01 | 5 | 2026-06-08 | 25 | 2026-07-13 | 2026-07-27 | ON TIME
FA-2-2000SL | 364732/W/H-Hold/Assy06/ Started/1 | 595518 | Mid-West Mfg. LLC | 09010630 | 364732 | STARTED | 2026-06-08 | 6 | 2026-06-15 | 2026-07-30 | 34 | 2000SL | ASSY06 | 364732 | STARTED | 2026-06-15 | 5 | 2026-06-22 | 25 | 2026-07-27 | 2026-08-10
FA-2-2000SL | 365274/W/H-Start/GenAssy/ Released/1 | 596256 | GERDAU AMERISTEEL WHITBY | 09010630 | 365274 |  | 2026-07-06 | 21 | 2026-07-13 | 2026-07-21 | 7 | 2000SL |  |  | Released | 2026-06-29 | 5 | 2026-07-06 | 25 | 2026-08-10 | 2026-08-24
FA-2-2000SL | 365341/W/H-Start/GenAssy/ Released/1 | 596498 | ACUREN | 09009410 | 365341 |  | 2026-07-13 | 6 | 2026-07-20 | 2026-09-03 | 34 | 1000SL |  |  | Released | 2026-07-13 | 5 | 2026-07-20 | 25 | 2026-08-24 | 2026-09-07
FA-2-2000SL | 365449/W/H-Start/GenAssy/ Released/1 | 596798 | PowerCept Middle East Mechanical & Engineering Equipment Trading LLC | 09010610 | 365449 |  | 2026-08-10 | 21 | 2026-08-17 | 2026-10-01 | 34 | 2000SL |  |  | Released | 2026-07-27 | 5 | 2026-08-03 | 25 | 2026-09-07 | 2026-09-21
FA-2-2000SL | 366476/W/H-Start/GenAssy/ Released/1 | 701140 | Jubail Energy Services Company | 09010610 | 366476 |  | 2026-08-17 | 6 | 2026-08-24 | 2026-11-30 | 71 | 2000SL |  |  | Released | 2026-08-10 | 5 | 2026-08-17 | 25 | 2026-09-21 | 2026-10-05
FA-2-2000SL | 365365/W/H-Start/GenAssy/ Released/1 | 596759 | Pacific Steel Group | 09010630 | 365365 |  | 2026-09-11 | 20 | 2026-09-18 | 2026-11-04 | 34 | 2000SL |  |  | Released | 2026-08-24 | 5 | 2026-08-31 | 25 | 2026-10-05 | 2026-10-19
FA-2-2000SL | 365908/W/H-Start/GenAssy/ Released/1 | 596794 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 09009410 | 365908 |  | 2026-09-21 | 7 | 2026-09-28 | 2026-11-13 | 35 | 1000SL |  |  | Released | 2026-09-07 | 5 | 2026-09-14 | 25 | 2026-10-19 | 2026-11-02
FA-2-2000SL | 365903/W/H-Start/GenAssy/ Released/1 | 596725 | ACUREN | 09009410 | 365903 |  | 2026-10-16 | 20 | 2026-10-23 | 2026-12-11 | 36 | 1000SL |  |  | Released | 2026-09-21 | 5 | 2026-09-28 | 25 | 2026-11-02 | 2026-11-16
FA-2-2000SL | 366045/W/H-Start/GenAssy/ Released/1 | 599466 | Jennmar Corporation of VA, Inc. | 09010600 | 366045 |  | 2026-10-27 | 8 | 2026-11-03 | 2026-12-23 | 37 | 2000SL |  |  | Released | 2026-10-05 | 5 | 2026-10-12 | 25 | 2026-11-16 | 2026-11-30
FA-MTLImps | 364994/Calib/Cal_GEN/ Started/1 | 596177 | Nucor Steel - Hertford | 12004060 | 364994 | STARTED | 2026-03-18 |  | 2026-03-25 | 2026-06-18 | 62 | IT542 | CAL | 364994 | STARTED | 2026-03-18 | 5 | 2026-03-25 | 25 | 2026-04-29 | 2026-05-13
FA-MTLImps | 365179/Paint/Paint/ Started/1 | 596576 | Steel Warehouse | 12004053 | 365179 | STARTED | 2026-05-14 | 42 | 2026-05-21 | 2026-06-29 | 28 | IT406 | PAINT | 365179 | STARTED | 2026-04-08 | 5 | 2026-04-15 | 25 | 2026-05-20 | 2026-06-03
FA-MTLImps | 366203/Assembly/Assy04/ Started/1 | 700524 | Nucor Towers and Structures | 12004053 | 366203 | STARTED | 2026-06-17 | 25 | 2026-06-24 | 2026-08-05 | 31 | IT406 | ASSY06 | 366203 | STARTED | 2026-04-29 | 5 | 2026-05-06 | 25 | 2026-06-10 | 2026-06-24
FA-MTLImps | 365451/W/H-Start/GenAssy/ Released/1 | 596952 | Tinius Olsen Testing Machine Shanghai Co Ltd | 12004051 | 365451 |  | 2026-07-08 | 16 | 2026-07-15 | 2026-08-20 | 27 | IT406 |  |  | Released | 2026-05-20 | 5 | 2026-05-27 | 25 | 2026-07-01 | 2026-07-15
FA-MTLImps | 366207/W/H-Start/GenAssy/ Released/1 | 700526 | Nucor Towers and Structures | 12004053 | 366207 |  | 2026-08-11 | 25 | 2026-08-18 | 2026-09-29 | 31 | IT406 |  |  | Released | 2026-06-10 | 5 | 2026-06-17 | 20 | 2026-07-15 | 2026-07-29
FA-MTLImps | 366479/W/H-Start/GenAssy/ Released/1 | 701140 | Jubail Energy Services Company | 12004062 | 366479 |  | 2026-09-10 | 23 | 2026-09-17 | 2026-10-30 | 32 | IT542 |  |  | Released | 2026-07-01 | 5 | 2026-07-08 | 20 | 2026-08-05 | 2026-08-19
FA-MTLImps | 365854/W/H-Start/GenAssy/ Released/1 | 596795 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 12004053 | 365854 |  | 2026-10-30 | 37 | 2026-11-06 | 2026-12-14 | 27 | IT406 |  |  | Released | 2026-07-22 | 5 | 2026-07-29 | 20 | 2026-08-26 | 2026-09-09
FA-MTLImps | 365855/W/H-Start/GenAssy/ Released/1 | 596795 | Salah & Musaad M. Al-Bassam Petroleum Equipment Company | 12004053 | 365855 |  | 2026-10-30 | 1 | 2026-11-06 | 2026-12-14 | 27 | IT406 |  |  | Released | 2026-08-12 | 5 | 2026-08-19 | 20 | 2026-09-16 | 2026-09-30
FA-MTLImps | 366211/W/H-Start/GenAssy/ Released/1 | 700528 | Nucor Steel Company | 12004053 | 366211 |  | 2026-11-24 | 18 | 2026-12-01 | 2027-01-15 | 34 | IT406 |  |  | Released | 2026-09-02 | 5 | 2026-09-09 | 20 | 2026-10-07 | 2026-10-21
FA-MTLImps | 366715/W/H-Start/GenAssy/ Created/1 | 701859 | North Star BlueScope Steel | 12004062 | 366715 | [6 empty] | IT542 |  |  |  | 2026-09-23 | 5 | 2026-09-30 | 20 | 2026-10-28 | 2026-11-11
[16 empty] | 2026-10-14 | 5 | 2026-10-21 | 20 | 2026-11-18 | 2026-12-02
[16 empty] | 2026-11-04 | 5 | 2026-11-11 | 20 | 2026-12-09 | 2026-12-23
[16 empty] | 2026-11-25 | 5 | 2026-12-02 | 20 | 2026-12-30 | 2027-01-13
[16 empty] | 2026-12-16 | 5 | 2026-12-23 | 20 | 2027-01-20 | 2027-02-03
Formulas:
ASSY START = WORKDAY([PRODUCTION START],[Pick])
ASSY END = WORKDAY([ASSY START],[Assy])
SHIP DATE = WORKDAY([ASSY END],10)
START CADENCE = NETWORKDAYS([PRODUCTION Start Date, row above],[PRODUCTION Start Date])
ASSY START DATE (+5 WK Days) = WORKDAY([PRODUCTION Start Date],5)
ASSY/CAL/COMPLETE DAYS = NETWORKDAYS([ASSY START DATE (+5 WK Days)],[PRODUCTION ORDER DELIVERY DATE])
PRODUCTION START = WORKDAY([PRODUCTION START, row above],10)